## Sheet1
ID | Work Item Type | Title | Assigned To | State | Tags | Original Estimate | Completed Work | Remaining Work | Changed Date | Created Date | Start Date | Due Date | Effort | Finish Date
1985 | Feature | JotForm Referral Integration | Patil, Nishiket <npatil@trustbridge.com> | Active |  |  |  |  | 2025-12-18 02:54 | 2025-03-18 08:59
3391 | User Story | Part 2 : As a developer I should verify that every referral email is autoaccepted | Patil, Nishiket <npatil@trustbridge.com> | New | Backend |  |  |  | 2025-12-18 03:03 | 2025-08-04 07:19
4419 | User Story | PROD readiness and bug fixing for v1.172 | Sachin Mehta <smehta@trustbridge.com> | Closed |  |  |  |  | 2025-12-17 02:38 | 2025-09-30 11:03
4458 | User Story | PROD releaes for v1.173 | Sachin Mehta <smehta@trustbridge.com> | Closed |  |  |  |  | 2025-12-18 02:37 | 2025-10-07 08:19
4610 | User Story | PROD release for version v1.174 | Sachin Mehta <smehta@trustbridge.com> | Closed | Frontend; Prod Support |  |  |  | 2025-12-22 05:17 | 2025-10-13 12:38
4824 | User Story | As a user I should not see mails with intake channel other | Patil, Nishiket <npatil@trustbridge.com> | Closed |  |  |  |  | 2025-12-18 02:52 | 2025-10-30 07:28
4838 | Bug | auto sign-in is taking time in SA. | Sumit Kumbhare <skumbhare@trustbridge.com> | Closed |  | 1 | 1 |  | 2025-12-16 04:29 | 2025-10-31 07:36
4848 | Task | Debugging the web view issue. | Sumit Kumbhare <skumbhare@trustbridge.com> | Closed |  | 2.5 | 2.5 |  | 2025-12-16 04:27 | 2025-11-03 00:33
4920 | User Story | Conduct Weekly BA Sync-up Call for "Sprint_2025_Q4_07" | Gawande, Ashwin <agawande@trustbridge.com> | New | Meeting; Planning |  |  |  | 2025-12-16 05:50 | 2025-11-05 06:34
5116 | User Story | As a user I should see F2F tag in the patient card | Patil, Nishiket <npatil@trustbridge.com> | New | Backend; Backlog; On Hold |  |  |  | 2025-12-18 02:52 | 2025-11-19 07:20
5174 | User Story | Part 4 : As a developer, I should investigate bugs in Jotform. | Chambhare, Tejasvinee <tchambhare@trustbridge.com> | Closed | Backend; Bug fixes; QA Passed |  |  |  | 2025-12-18 02:59 | 2025-11-24 08:04
5179 | Bug | There is a delay in showing the visit under Admission Teams after clicking on the Patient tab. | Bahulashwa Kamble <bkamble@trustbridge.com> | Resolved | Prod Issue | 8 | 5 | 3 | 2025-12-17 02:00 | 2025-11-24 08:33
5281 | User Story | View/Update Employee Storm preference details in portal | Jain, Sakshi <sjain@trustbridge.com> | New | Frontend |  |  |  | 2025-12-15 01:08 | 2025-11-27 03:15
5300 | Issue | Time discrepancy in virtualCare while creating call. | Kadam, Mithilesh <mkadam@trustbridge.com> | Closed |  |  |  |  | 2025-12-16 04:38 | 2025-11-28 04:44
5309 | Task | Code review: Issue_5300 | Sachin Mehta <smehta@trustbridge.com> | Closed |  | 2 | 4 |  | 2025-12-17 10:51 | 2025-11-28 09:53
5360 | User Story | SPIKE: As a developer, I need to provide support for filtering out patients by patient id in the patient Search API and investigate the late referrals issue. | Soni, Twarit <tsoni@trustbridge.com> | Closed | Backend; Prod Support |  |  |  | 2025-12-16 10:34 | 2025-12-03 02:01
5361 | User Story | Part 1- As a developer, I should Refine Intake Sources for accurate Intake Channel classification | Chambhare, Tejasvinee <tchambhare@trustbridge.com> | Closed | QA Validation |  |  |  | 2025-12-16 04:32 | 2025-12-03 02:13
5364 | Bug | The alignment for email is not consistence | Gawande, Ashwin <agawande@trustbridge.com> | New |  |  |  |  | 2025-12-17 02:14 | 2025-12-03 02:50
5365 | User Story | Part B: Enhancing Wireframe for DC Storm Emergency Preparation portal based on feedback. | Gawande, Ashwin <agawande@trustbridge.com> | Closed |  |  |  |  | 2025-12-18 00:07 | 2025-12-03 03:20
5369 | Task | Need to update the DigitalCare roadmap on Production for Sprint_2025_Q4_06 | Gawande, Ashwin <agawande@trustbridge.com> | Closed |  | 8 | 12 |  | 2025-12-16 05:21 | 2025-12-03 03:25
5370 | User Story | Monitoring and Updating Feature Roadmap for "Sprint_2025_Q4_06" | Gawande, Ashwin <agawande@trustbridge.com> | Closed | Planning; Requirement Grooming |  |  |  | 2025-12-16 05:28 | 2025-12-03 03:26
5377 | Task | Collating all updates in PPT for technical sync-up meeting 12/17 | Gawande, Ashwin <agawande@trustbridge.com> | Closed | Planning | 2 | 2 |  | 2025-12-17 23:58 | 2025-12-03 03:28
5378 | Task | Conducting Technical Sync-up call with Client 12/17 | Gawande, Ashwin <agawande@trustbridge.com> | Closed | Meeting | 1 | 1 |  | 2025-12-17 23:59 | 2025-12-03 03:28
5380 | User Story | Technical Sync-up Team Meeting for sprint "Sprint_2025_Q4_06" | Gawande, Ashwin <agawande@trustbridge.com> | Closed | Meeting; Planning |  |  |  | 2025-12-16 05:29 | 2025-12-03 03:33
5381 | User Story | Regular Task Updates for Independent Teammates for sprint "Sprint_2025_Q4_06" | Gawande, Ashwin <agawande@trustbridge.com> | Closed | Meeting |  |  |  | 2025-12-16 05:29 | 2025-12-03 04:42
5382 | Bug | Other source received from trustbridge domain. | Patil, Nishiket <npatil@trustbridge.com> | Closed |  | 1 | 1 | 0 | 2025-12-16 04:43 | 2025-12-03 04:45
5384 | Task | Conduct Common Scrum for 12/15 | Gawande, Ashwin <agawande@trustbridge.com> | Closed | Meeting; Planning | 0.5 | 0.5 |  | 2025-12-16 05:48 | 2025-12-03 05:05
5391 | Task | Conduct Common Scrum for 12/11 | Gawande, Ashwin <agawande@trustbridge.com> | Closed | Meeting; Planning | 0.5 | 0.5 |  | 2025-12-16 05:31 | 2025-12-03 05:05
5392 | Task | Conduct Common Scrum for 12/16 | Gawande, Ashwin <agawande@trustbridge.com> | Closed | Meeting; Planning | 0.5 | 0.5 |  | 2025-12-16 05:31 | 2025-12-03 05:05
5393 | User Story | Scrum Planning and Team Meeting for sprint "Sprint_2025_Q4_06" | Gawande, Ashwin <agawande@trustbridge.com> | Closed | Meeting; Planning |  |  |  | 2025-12-16 05:49 | 2025-12-03 05:11
5395 | User Story | Weekly Team Session: Process Learnings & Insights for Sprint "Sprint_2022_Q4_06" | Gawande, Ashwin <agawande@trustbridge.com> | Closed | Meeting; Planning |  |  |  | 2025-12-16 05:59 | 2025-12-03 05:13
5396 | User Story | [Part2]: AI narrative feedback from the client | Patel, Hetal <hpatel@trustbridge.com> | Closed | Testing Done |  |  |  | 2025-12-17 10:56 | 2025-12-03 05:18
5397 | User Story | [Part2]: As a user, view a list of items that are categorized as “Not a Referral” within the Referral Queue. | Patel, Hetal <hpatel@trustbridge.com> | Closed | Code Review Done; QA; Testing Done |  |  |  | 2025-12-17 10:59 | 2025-12-03 05:22
5398 | User Story | [Part2]: As a user, see admission-related tags on the Patient Detail same as patient card. | Patel, Hetal <hpatel@trustbridge.com> | Closed | Code Review Done; QA |  |  |  | 2025-12-17 10:57 | 2025-12-03 05:26
5401 | User Story | Trustbridge referral monitoring Q4-06 | Patil, Nishiket <npatil@trustbridge.com> | Closed | monitoring |  |  |  | 2025-12-18 00:33 | 2025-12-03 07:53
5421 | User Story | Daily sanity on producion for the Sprint_2025_Q4_06 | Chambhare, Tejasvinee <tchambhare@trustbridge.com> | Closed | QA Validation |  |  |  | 2025-12-18 08:06 | 2025-12-04 06:07
5422 | User Story | Part-1: Add Fallback to Microsoft Entra ID in AD Helper | Soni, Twarit <tsoni@trustbridge.com> | Closed | Backend; Prod Support |  |  |  | 2025-12-17 04:59 | 2025-12-04 06:11
5435 | Task | Need to verify historical completed referral based on completedAt time. | Chambhare, Tejasvinee <tchambhare@trustbridge.com> | Closed | QA Passed; QA Validation | 3 | 3 |  | 2025-12-16 03:32 | 2025-12-05 05:03
5444 | User Story | [Part-2]Write automation script for referral tab | Bahulashwa Kamble <bkamble@trustbridge.com> | Closed |  |  |  |  | 2025-12-17 01:54 | 2025-12-08 02:07
5446 | User Story | Production Support-Sprint_2025_Q4_06 | Bahulashwa Kamble <bkamble@trustbridge.com> | Closed | Prod Support |  |  |  | 2025-12-17 01:59 | 2025-12-08 02:08
5450 | User Story | As a Manager I can Add and Edit Employee storm assignments | Jain, Sakshi <sjain@trustbridge.com> | Active | Backend; Frontend |  |  |  | 2025-12-17 05:10 | 2025-12-08 02:19
5451 | User Story | Part 4: As a technical upgrade, I want to Upgrade Angular Framework to Version 18 | Kadam, Mithilesh <mkadam@trustbridge.com> | Closed | Frontend |  |  |  | 2025-12-17 02:22 | 2025-12-08 02:28
5456 | User Story | [Part 1]: As a user, view a list of items that are categorized as “Not a Referral” within the teams. | Patel, Hetal <hpatel@trustbridge.com> | Closed | Code Review Done; QA; Testing Done |  |  |  | 2025-12-17 11:01 | 2025-12-08 04:53
5457 | User Story | [Part 1]: As a User, able to search based on date range & assignee in the teams. | Patel, Hetal <hpatel@trustbridge.com> | Closed |  |  |  |  | 2025-12-17 01:16 | 2025-12-08 04:54
5459 | Task | PART - 3 As a developer, Need to Create CRUD API for Employee Management. | Sharma, Hemant <hsharma@trustbridge.com> | Closed | Backend | 20 | 34 |  | 2025-12-15 11:12 | 2025-12-08 06:02
5461 | Task | Part 2 Duplicate agency populated for impacted agency | Sharma, Hemant <hsharma@trustbridge.com> | New | Backend; Backlog | 4 | 0 | 4 | 2025-12-17 05:14 | 2025-12-08 06:06
5463 | Task | Brush up Java topics to automate emergency prep | Konika Jamgade <kjamgade@trustbridge.com> | Closed |  | 14 | 10 |  | 2025-12-19 05:26 | 2025-12-08 07:56
5475 | Task | [Dev] Part A: Resolve UI issues in other routes | Kadam, Mithilesh <mkadam@trustbridge.com> | Closed | Frontend | 16 | 16 |  | 2025-12-16 02:36 | 2025-12-09 01:10
5485 | Task | Perform sanity on production on 12/09/2025 | Bahulashwa Kamble <bkamble@trustbridge.com> | Closed | Prod Support | 2 | 0 |  | 2025-12-16 02:48 | 2025-12-09 02:29
5488 | User Story | As a developer I should move trustbridge Mailbox to prod | Patil, Nishiket <npatil@trustbridge.com> | Closed |  |  |  |  | 2025-12-15 04:31 | 2025-12-09 04:35
5494 | Task | Understand & documentation for design & technical requirement. | Patel, Hetal <hpatel@trustbridge.com> | Closed |  | 6 | 5 |  | 2025-12-18 06:44 | 2025-12-09 11:39
5498 | Task | QA employee preference form | Konika Jamgade <kjamgade@trustbridge.com> | Closed |  | 3 | 3 |  | 2025-12-19 05:28 | 2025-12-10 02:34
5499 | Task | KT session for Digital care - Workforce | Konika Jamgade <kjamgade@trustbridge.com> | Closed |  | 1 | 1 |  | 2025-12-19 05:28 | 2025-12-10 02:38
5501 | Task | Referral validation for trustbridge after mailbox creation - 09 December | Patil, Nishiket <npatil@trustbridge.com> | Closed |  | 1 | 1 |  | 2025-12-15 04:31 | 2025-12-10 06:06
5504 | User Story | SPIKE: As a developer, I need to investigate the production issues in MAC and Crisis Care. | Soni, Twarit <tsoni@trustbridge.com> | Closed | Backend; Prod Support |  |  |  | 2025-12-16 10:33 | 2025-12-10 08:59
5508 | User Story | Conduct KT Session and QA Discussion Call. | Chambhare, Tejasvinee <tchambhare@trustbridge.com> | Closed | QA |  |  |  | 2025-12-18 08:06 | 2025-12-11 01:15
5515 | Task | Add scenarios in workforce which was discussed in demo call. | Bahulashwa Kamble <bkamble@trustbridge.com> | Closed |  | 8 | 8 |  | 2025-12-16 02:56 | 2025-12-11 07:52
5516 | Task | Working on the Issues found during testing. | Sumit Kumbhare <skumbhare@trustbridge.com> | Active |  |  |  |  | 2025-12-16 04:25 | 2025-12-12 01:29
5518 | Task | QA- able to search based on date range & assignee in the teams. | Chambhare, Tejasvinee <tchambhare@trustbridge.com> | Closed |  | 1 |  |  | 2025-12-17 01:16 | 2025-12-12 03:13
5521 | Task | QA- Testing “Not a Referral” within the teams. | Chambhare, Tejasvinee <tchambhare@trustbridge.com> | Closed | QA Passed; QA Validation | 3 | 3 |  | 2025-12-15 06:03 | 2025-12-15 00:57
5522 | Task | As a developer need to create an api to view and update the storm preference details. | Sharma, Hemant <hsharma@trustbridge.com> | Closed | Backend | 5 |  |  | 2025-12-17 05:13 | 2025-12-15 01:05
5523 | Bug | In the Workforce tab, for the Current Shift filter, completed shifts are also being displayed. | Chambhare, Tejasvinee <tchambhare@trustbridge.com> | Closed |  |  |  |  | 2025-12-18 07:57 | 2025-12-15 03:19
5524 | User Story | As a developer, I should investigate why HMC referral was visible in referral queu for TB user | Patil, Nishiket <npatil@trustbridge.com> | Closed |  |  |  |  | 2025-12-15 04:35 | 2025-12-15 04:32
5525 | Task | Investigation for US 5224 investigate why HMC referral was visible in referral queue for TB user | Patil, Nishiket <npatil@trustbridge.com> | Closed |  | 4 | 5 |  | 2025-12-15 04:35 | 2025-12-15 04:34
5526 | User Story | As a user, I should be able to see extracted information from document of referral faxes | Patil, Nishiket <npatil@trustbridge.com> | Closed |  |  |  |  | 2025-12-18 00:33 | 2025-12-15 04:39
5527 | Task | Creating a technical implementation plan with gaurav | Patil, Nishiket <npatil@trustbridge.com> | Closed |  | 8 | 8 |  | 2025-12-18 00:30 | 2025-12-15 04:40
5529 | Task | As a developer need to create/update API for storm assignment | Sharma, Hemant <hsharma@trustbridge.com> | Closed | Backend | 16 | 14 |  | 2025-12-17 05:10 | 2025-12-15 05:05
5530 | Task | Performed Daily prod Sanity- Dec 15 | Chambhare, Tejasvinee <tchambhare@trustbridge.com> | Closed |  | 2 | 2 |  | 2025-12-15 06:02 | 2025-12-15 06:00
5531 | Task | KT session for Harshal | Chambhare, Tejasvinee <tchambhare@trustbridge.com> | Closed | QA | 2 | 2 |  | 2025-12-15 06:43 | 2025-12-15 06:42
5532 | Task | [Dev]: Implement code review suggestions. | Soni, Twarit <tsoni@trustbridge.com> | Closed | Backend | 7 | 7 |  | 2025-12-15 09:57 | 2025-12-15 07:58
5533 | Task | [Code Review]: US 5422 (Entra Id fallback in AD helper class) | Meshram's, Swapnil <smeshram@trustbridge.com> | New | Backend; Code Review |  |  |  | 2025-12-17 04:56 | 2025-12-15 07:58
5534 | Task | Implementation for date & assignee filter in referral teams. | Patel, Hetal <hpatel@trustbridge.com> | Closed |  | 12 | 2 |  | 2025-12-17 11:06 | 2025-12-15 11:33
5535 | Task | Duplicate comment issue received by mail. | Patel, Hetal <hpatel@trustbridge.com> | Closed |  | 5 | 5 |  | 2025-12-15 11:40 | 2025-12-15 11:38
5536 | Task | KT session with sumit for SA development | Sachin Mehta <smehta@trustbridge.com> | Closed |  | 1 | 1 |  | 2025-12-15 12:10 | 2025-12-15 12:10
5537 | Task | Code review : US_5456 | Sachin Mehta <smehta@trustbridge.com> | Closed |  | 2 | 2 |  | 2025-12-15 12:13 | 2025-12-15 12:13
5538 | Task | Code setup and session on Curser AI | Sachin Mehta <smehta@trustbridge.com> | Closed |  | 4 | 6 |  | 2025-12-15 12:15 | 2025-12-15 12:15
5539 | Task | Performed daily sanity- Dec 16 | Chambhare, Tejasvinee <tchambhare@trustbridge.com> | Closed | QA Passed; QA Validation | 3 | 3 |  | 2025-12-16 02:44 | 2025-12-16 00:56
5540 | Bug | Referral Queue – Filters Applied Automatically When Toggle Is Enabled Without Clicking Search. | Patel, Hetal <hpatel@trustbridge.com> | New | Prod Issue |  |  |  | 2025-12-16 10:34 | 2025-12-16 01:24
5541 | Bug | Filter Is Applied for Completed Referrals Without Clicking Search. | Patel, Hetal <hpatel@trustbridge.com> | New | Prod Issue |  |  |  | 2025-12-17 11:11 | 2025-12-16 01:34
5542 | Bug | Virtual Care – Closed Tasks Toggle Shows Empty List Despite Available Done Tasks | Chambhare, Tejasvinee <tchambhare@trustbridge.com> | Closed |  |  |  |  | 2025-12-18 07:53 | 2025-12-16 02:19
5543 | Task | [Dev]: Implement Ag-grid in crisis-care table | Kadam, Mithilesh <mkadam@trustbridge.com> | Closed | Frontend | 8 | 8 |  | 2025-12-17 01:57 | 2025-12-16 02:37
5544 | Task | QA-Testing of “Not a Referral” within the teams on 5021. | Chambhare, Tejasvinee <tchambhare@trustbridge.com> | Closed | QA Passed; QA Validation | 2 | 2 |  | 2025-12-16 05:31 | 2025-12-16 02:52
5545 | Task | Explore Git | Bahulashwa Kamble <bkamble@trustbridge.com> | Closed |  | 1 | 1 |  | 2025-12-17 01:53 | 2025-12-16 02:57
5546 | Task | When Toggle Is Enabled Without Clicking Search, Filters Applied Automatically. | Patel, Hetal <hpatel@trustbridge.com> | New |  |  |  |  | 2025-12-16 03:30 | 2025-12-16 03:27
5548 | Task | Need to reproduce weight loss AI related feedback on UAT. | Chambhare, Tejasvinee <tchambhare@trustbridge.com> | Closed | QA Passed; QA Validation | 4 | 4 |  | 2025-12-16 08:21 | 2025-12-16 04:31
5549 | User Story | Implement agency-based filter for IPU Bed Board list(Shift Assistant) | Sumit Kumbhare <skumbhare@trustbridge.com> | Active |  |  |  |  | 2025-12-18 08:22 | 2025-12-16 04:37
5550 | Task | Design & implement Agency Filter dialog UI | Sumit Kumbhare <skumbhare@trustbridge.com> | Closed |  | 2 | 2 |  | 2025-12-16 04:43 | 2025-12-16 04:41
5551 | Task | Parse & validate agency data from IPU Bed Board API | Sumit Kumbhare <skumbhare@trustbridge.com> | Closed |  | 2 | 2 |  | 2025-12-16 04:44 | 2025-12-16 04:44
5552 | Task | Implement agency-based filtering logic in ViewModel | Sumit Kumbhare <skumbhare@trustbridge.com> | Closed |  | 2 | 2 |  | 2025-12-16 04:45 | 2025-12-16 04:44
5553 | Task | Integrate agency filter with IPU list UI | Sumit Kumbhare <skumbhare@trustbridge.com> | Closed |  |  |  |  | 2025-12-16 04:46 | 2025-12-16 04:45
5554 | User Story | Need to validate the scenario in MAC AI summary generation when only past weight is changed and now weight is blank. | Chambhare, Tejasvinee <tchambhare@trustbridge.com> | Closed |  |  |  |  | 2025-12-18 08:05 | 2025-12-16 04:46
5555 | Task | Edge case handling & UX polish | Sumit Kumbhare <skumbhare@trustbridge.com> | Closed |  | 3.5 | 3.5 |  | 2025-12-17 03:21 | 2025-12-16 04:47
5556 | User Story | Technical Sync-up Team Meeting for sprint "Sprint_2025_Q4_07" | Gawande, Ashwin <agawande@trustbridge.com> | Active | Meeting; Planning |  |  |  | 2025-12-17 23:59 | 2025-12-16 05:24
5557 | User Story | Monitoring and Updating Feature Roadmap for "Sprint_2025_Q4_07" | Gawande, Ashwin <agawande@trustbridge.com> | Active | Planning; Requirement Grooming |  |  |  | 2025-12-17 23:59 | 2025-12-16 05:25
5558 | Task | Need to update the DigitalCare roadmap on Production for Sprint_2025_Q4_07 | Gawande, Ashwin <agawande@trustbridge.com> | Active |  | 8 | 1 | 7 | 2025-12-19 01:57 | 2025-12-16 05:26
5559 | User Story | Regular Task Updates from Independent Team/Teammates for sprint "Sprint_2025_Q4_07" | Gawande, Ashwin <agawande@trustbridge.com> | Active | Meeting |  |  |  | 2025-12-22 00:27 | 2025-12-16 05:29
5560 | Task | Conduct a call to collect feedback and other recent observation 12/16 | Gawande, Ashwin <agawande@trustbridge.com> | Closed | Meeting | 1 | 1 |  | 2025-12-16 05:59 | 2025-12-16 05:59
5561 | Task | Emergency Storm Portal ¦ Internal Progress Update 12/16 | Gawande, Ashwin <agawande@trustbridge.com> | Closed | Meeting; Planning | 1 | 1 |  | 2025-12-17 00:33 | 2025-12-16 06:00
5562 | Bug | The drop down is opening away from the input field | Jain, Sakshi <sjain@trustbridge.com> | New |  |  |  |  | 2025-12-16 07:48 | 2025-12-16 07:46
5563 | Bug | The font size is not aligned in employee preference | Jain, Sakshi <sjain@trustbridge.com> | New |  |  |  |  | 2025-12-16 08:10 | 2025-12-16 08:00
5564 | Task | Investigate & update the AI prompt for past weight scenario. | Patel, Hetal <hpatel@trustbridge.com> | Closed |  | 3 | 3 |  | 2025-12-16 10:28 | 2025-12-16 10:26
5565 | Task | [Deployment]: To deploy backend services in UAT for Entra Id fallback in AD helper. | Soni, Twarit <tsoni@trustbridge.com> | Closed | Backend; Deployment | 6 | 6 |  | 2025-12-16 10:42 | 2025-12-16 10:38
5566 | User Story | [Part 2]: As a User, able to search based on date range & assignee in the teams. | Patel, Hetal <hpatel@trustbridge.com> | Resolved | Code Review Done; QA; Testing Done |  |  |  | 2025-12-18 06:44 | 2025-12-17 01:15
5567 | Task | QA- able to search based on date range & assignee in the teams. | Chambhare, Tejasvinee <tchambhare@trustbridge.com> | Closed | QA Passed; QA Validation | 2 | 2 |  | 2025-12-18 01:02 | 2025-12-17 01:18
5568 | Task | QA- agency-based filter for IPU Bed Board list(Shift Assistant). | Chambhare, Tejasvinee <tchambhare@trustbridge.com> | Closed | QA Passed; QA Validation | 2 | 2 |  | 2025-12-18 08:25 | 2025-12-17 01:43
5569 | Task | IPU Tag not visible properly on UAT whereas PROD is showing correctly | Sachin Mehta <smehta@trustbridge.com> | Closed |  | 4 | 8 |  | 2025-12-17 01:55 | 2025-12-17 01:54
5570 | User Story | Production Support-\Sprint_2025_Q4_07 | Bahulashwa Kamble <bkamble@trustbridge.com> | Active |  |  |  |  | 2025-12-17 02:02 | 2025-12-17 02:01
5571 | User Story | Automate Clinical Queue module | Bahulashwa Kamble <bkamble@trustbridge.com> | New |  |  |  |  | 2025-12-17 02:05 | 2025-12-17 02:05
5572 | User Story | Part 5: As a technical upgrade, I want to Upgrade Angular Framework to Version 18 | Kadam, Mithilesh <mkadam@trustbridge.com> | New | Frontend |  |  |  | 2025-12-17 02:21 | 2025-12-17 02:20
5573 | Task | Update regression test cases for 8 to 18 angular upgrade testing | Bahulashwa Kamble <bkamble@trustbridge.com> | Active | QA | 3 | 0 | 3 | 2025-12-17 02:26 | 2025-12-17 02:24
5574 | Task | Unable to route to the employee-preference form directly when not authenticated | Sachin Mehta <smehta@trustbridge.com> | Closed |  | 2 | 4 |  | 2025-12-17 11:51 | 2025-12-17 02:50
5575 | User Story | Part-2: Add Fallback to Microsoft Entra ID in AD Helper. | Soni, Twarit <tsoni@trustbridge.com> | Active | Backend; Prod Support |  |  |  | 2025-12-18 09:18 | 2025-12-17 04:55
5576 | Task | QA- Need to verify AD migrated users API for all modules. | Chambhare, Tejasvinee <tchambhare@trustbridge.com> | Closed | QA Validation | 6 | 6 |  | 2025-12-19 08:13 | 2025-12-17 05:09
5577 | User Story | PART - 2 As a Manager I can Add and Edit Employee storm assignments | Jain, Sakshi <sjain@trustbridge.com> | Active | Backend; Frontend |  |  |  | 2025-12-17 05:13 | 2025-12-17 05:11
5578 | Task | As a developer, Build Update and Get Ess workforce assignment API | Sharma, Hemant <hsharma@trustbridge.com> | Active | Backend | 16 | 4 | 12 | 2025-12-19 09:47 | 2025-12-17 05:13
5579 | Task | [Dev]: Implement fixes for GetPhoto API, Reduce batch size for graph API and Add test Dev usernames. | Soni, Twarit <tsoni@trustbridge.com> | Closed | Backend | 7 | 7 |  | 2025-12-17 11:45 | 2025-12-17 07:15
5580 | User Story | [Part3]: As a user, view a list of items that are categorized as “Not a Referral” within the Referral Queue. | Patel, Hetal <hpatel@trustbridge.com> | Resolved | Code Review Done; QA; Testing Done |  |  |  | 2025-12-18 06:45 | 2025-12-17 10:53
5581 | User Story | [Part3]: AI narrative feedback from the client | Patel, Hetal <hpatel@trustbridge.com> | Resolved | Testing Done |  |  |  | 2025-12-19 05:36 | 2025-12-17 10:56
5582 | User Story | [Part3]: As a user, see admission-related tags on the Patient Detail same as patient card. | Patel, Hetal <hpatel@trustbridge.com> | Resolved | Code Review Done; QA |  |  |  | 2025-12-18 06:44 | 2025-12-17 10:58
5583 | User Story | [Part 2]: As a user, view a list of items that are categorized as “Not a Referral” within the teams. | Patel, Hetal <hpatel@trustbridge.com> | Resolved | Code Review Done; QA; Testing Done |  |  |  | 2025-12-17 11:02 | 2025-12-17 11:01
5587 | Task | [Dev]: Implementation for date & assignee filter in referral teams. | Patel, Hetal <hpatel@trustbridge.com> | Closed |  | 8 | 8 |  | 2025-12-17 11:09 | 2025-12-17 11:09
5588 | Task | Code Review: US_5457 & US_5566 | Sachin Mehta <smehta@trustbridge.com> | Closed |  | 2 | 2.5 |  | 2025-12-17 11:56 | 2025-12-17 11:55
5589 | User Story | Part C: Enhancing Wireframe for DC Storm Emergency Preparation portal based on feedback. | Gawande, Ashwin <agawande@trustbridge.com> | Active |  |  |  |  | 2025-12-22 00:30 | 2025-12-18 00:03
5590 | Task | Conduct Common Scrum for 12/17 | Gawande, Ashwin <agawande@trustbridge.com> | Closed | Meeting; Planning | 0.5 | 0.5 |  | 2025-12-18 00:12 | 2025-12-18 00:10
5591 | User Story | Scrum Planning and Team Meeting for sprint "Sprint_2025_Q4_07" | Gawande, Ashwin <agawande@trustbridge.com> | Active | Meeting; Planning |  |  |  | 2025-12-18 00:16 | 2025-12-18 00:12
5592 | Task | Conduct Common Scrum for 12/18 | Gawande, Ashwin <agawande@trustbridge.com> | Closed | Meeting; Planning | 0.5 | 0.5 |  | 2025-12-18 00:16 | 2025-12-18 00:13
5593 | Task | Conduct Common Scrum for 12/19 | Gawande, Ashwin <agawande@trustbridge.com> | Closed | Meeting; Planning | 0.5 | 0.5 |  | 2025-12-19 05:35 | 2025-12-18 00:16
5594 | Task | Conduct Common Scrum for 12/22 | Gawande, Ashwin <agawande@trustbridge.com> | Closed | Meeting; Planning | 0.5 | 0.5 |  | 2025-12-22 00:23 | 2025-12-18 00:16
5595 | Task | Conduct Common Scrum for 12/23 | Gawande, Ashwin <agawande@trustbridge.com> | New | Meeting; Planning | 0.5 |  | 0.5 | 2025-12-18 00:17 | 2025-12-18 00:17
5596 | Task | Conduct Common Scrum for 12/24 | Gawande, Ashwin <agawande@trustbridge.com> | New | Meeting; Planning | 0.5 |  | 0.5 | 2025-12-18 00:18 | 2025-12-18 00:18
5597 | Task | Conduct Common Scrum for 12/26 | Gawande, Ashwin <agawande@trustbridge.com> | New | Meeting; Planning | 0.5 |  | 0.5 | 2025-12-18 00:20 | 2025-12-18 00:18
5598 | Task | Conduct Common Scrum for 12/29 | Gawande, Ashwin <agawande@trustbridge.com> | New | Meeting; Planning | 0.5 |  | 0.5 | 2025-12-18 00:23 | 2025-12-18 00:21
5599 | Task | Conduct Common Scrum for 12/30 | Gawande, Ashwin <agawande@trustbridge.com> | New | Meeting; Planning | 0.5 |  | 0.5 | 2025-12-18 00:22 | 2025-12-18 00:22
5600 | Task | Emergency Storm Portal ¦ Internal Progress Update 12/18 | Gawande, Ashwin <agawande@trustbridge.com> | Closed | Meeting; Planning | 1 | 2 |  | 2025-12-18 07:57 | 2025-12-18 00:28
5601 | Task | Winterfell ¦ Internal Progress Updates 12/17 | Gawande, Ashwin <agawande@trustbridge.com> | Closed | Meeting | 1 | 1.5 |  | 2025-12-18 00:30 | 2025-12-18 00:29
5602 | User Story | As a user, I should be able to see document types from document of referral faxes | Patil, Nishiket <npatil@trustbridge.com> | Active |  |  |  |  | 2025-12-19 09:06 | 2025-12-18 00:33
5603 | Task | [DEV] : Classify the documents using azure doc intelligence and add documentType tag and publish classified and unclassified events | Patil, Nishiket <npatil@trustbridge.com> | Closed |  | 16 | 17 |  | 2025-12-19 09:05 | 2025-12-18 00:37
5604 | User Story | As a developer, I should Investigate why expiration mails from azure for empath tenants are not being received | Patil, Nishiket <npatil@trustbridge.com> | Active |  |  |  |  | 2025-12-18 00:43 | 2025-12-18 00:40
5605 | Task | Investigate for US5604 | Patil, Nishiket <npatil@trustbridge.com> | Active |  | 6 | 3 | 3 | 2025-12-18 00:42 | 2025-12-18 00:40
5606 | Task | UAT Testing and Release preparation. | Chambhare, Tejasvinee <tchambhare@trustbridge.com> | Closed | QA Passed; QA Validation | 5 | 5 |  | 2025-12-18 08:02 | 2025-12-18 01:03
5607 | Bug | Filter option is displayed in patient tab also. | Patel, Hetal <hpatel@trustbridge.com> | Resolved |  | 1 | 1 | 0 | 2025-12-18 06:42 | 2025-12-18 01:33
5608 | Bug | User is unable to search referral via patient name and MRN. (Completed & not a referral) | Patel, Hetal <hpatel@trustbridge.com> | Resolved | Frontend | 2 | 2 | 0 | 2025-12-18 06:42 | 2025-12-18 01:56
5609 | User Story | As a developer, I should have a understanding of CDC listener | Patil, Nishiket <npatil@trustbridge.com> | New |  |  |  |  | 2025-12-18 03:03 | 2025-12-18 02:49
5610 | User Story | Part 5 : As a developer, I need to plan to move Jotform implementation to production | Patil, Nishiket <npatil@trustbridge.com> | New | Backend; Client Dependent |  |  |  | 2025-12-18 03:04 | 2025-12-18 03:03
5611 | User Story | User should be view map Map view for patient & facility in Emergency preparation dashboard | Sachin Mehta <smehta@trustbridge.com> | Active |  |  |  |  | 2025-12-18 11:17 | 2025-12-18 05:08
5612 | User Story | [Part 1]: As a developer, Ability to understand & discuss the client requirements (By Dr. chen). | Patel, Hetal <hpatel@trustbridge.com> | Active | Doc creation; Requirement Grooming |  |  |  | 2025-12-18 06:51 | 2025-12-18 06:47
5613 | Task | Requirement grooming & understanding. | Patel, Hetal <hpatel@trustbridge.com> | Active |  | 10 | 3 | 5 | 2025-12-18 06:57 | 2025-12-18 06:52
5614 | Task | Go no go meeting for v179.3 UAT release. | Patel, Hetal <hpatel@trustbridge.com> | Closed |  | 1 | 1 |  | 2025-12-18 07:19 | 2025-12-18 07:08
5615 | Task | Reviewing and sharing Admission teams user manual with Delia and team | Gawande, Ashwin <agawande@trustbridge.com> | Closed |  | 1 | 2 |  | 2025-12-18 08:00 | 2025-12-18 07:59
5616 | User Story | Part 1-Need to validate the scenario in MAC AI summary generation when only past weight is changed and now weight is blank. | Chambhare, Tejasvinee <tchambhare@trustbridge.com> | Active |  |  |  |  | 2025-12-18 08:00 | 2025-12-18 08:00
5617 | Task | Collating all updates in PPT for technical sync-up meeting 12/19 | Gawande, Ashwin <agawande@trustbridge.com> | Closed | Planning | 2 | 2 |  | 2025-12-22 00:19 | 2025-12-18 08:05
5618 | Task | Conducting Technical Sync-up call with Client 12/19 | Gawande, Ashwin <agawande@trustbridge.com> | Closed | Meeting | 1 | 1 |  | 2025-12-22 00:21 | 2025-12-18 08:06
5619 | Task | Review UAT release 1.179.3 | Gawande, Ashwin <agawande@trustbridge.com> | Closed |  | 1 | 2.5 |  | 2025-12-18 08:10 | 2025-12-18 08:10
5621 | User Story | SPIKE: As a developer, I need to provide PPS score logic details to stakeholders. | Soni, Twarit <tsoni@trustbridge.com> | Closed | Backend; Prod Support |  |  |  | 2025-12-18 09:34 | 2025-12-18 09:19
5622 | Task | [R&D]: To fetch the PPS score logic from Patient Vital Sign API and extract SQL query from it. | Soni, Twarit <tsoni@trustbridge.com> | Closed | Backend | 5 | 5 |  | 2025-12-18 09:33 | 2025-12-18 09:31
5623 | Task | [Dev]: Implement functionality to fetch the AD groups from both tenant of Trustbridge workforces. | Soni, Twarit <tsoni@trustbridge.com> | New | Backend | 12 |  |  | 2025-12-18 09:37 | 2025-12-18 09:35
5624 | Task | integrating MAP basic structure | Sachin Mehta <smehta@trustbridge.com> | Closed |  | 8 | 8 |  | 2025-12-18 12:48 | 2025-12-18 11:18
5625 | Task | UAT release for v1.179.3 | Sachin Mehta <smehta@trustbridge.com> | Closed |  | 1 | 1 |  | 2025-12-18 12:49 | 2025-12-18 12:49
5626 | Task | Create user manual document for admission teams | Bahulashwa Kamble <bkamble@trustbridge.com> | Closed |  | 4 | 4 |  | 2025-12-19 00:55 | 2025-12-19 00:55
5627 | Task | code review for IPU bed board agency filter implementation. | Sumit Kumbhare <skumbhare@trustbridge.com> | Active |  | 2 |  |  | 2025-12-19 00:59 | 2025-12-19 00:59
5628 | User Story | Create new Shift Assistant build v1.25 and v0.132 | Sumit Kumbhare <skumbhare@trustbridge.com> | Closed |  |  |  |  | 2025-12-19 01:34 | 2025-12-19 01:03
5629 | Task | Updated TB (v0.132) and Empath (v1.25) application versions | Sumit Kumbhare <skumbhare@trustbridge.com> | Closed |  | 1 | 1 |  | 2025-12-19 01:33 | 2025-12-19 01:32
5630 | Task | Verify shift assistant test and shift assistant test and share the build with Mohammed | Bahulashwa Kamble <bkamble@trustbridge.com> | Closed | QA | 3 | 3 |  | 2025-12-19 02:05 | 2025-12-19 02:04
5631 | Bug | Unable to create a new storm season | Konika Jamgade <kjamgade@trustbridge.com> | Closed | Backend | 1 | 0.2 | 0 | 2025-12-19 05:46 | 2025-12-19 05:23
5632 | Task | Part 2: Brush up Java topics to automate emergency prep | Konika Jamgade <kjamgade@trustbridge.com> | Active |  | 14 | 10 | 4 | 2025-12-19 05:29 | 2025-12-19 05:26
5633 | Task | Part 2: QA employee preference form - | Konika Jamgade <kjamgade@trustbridge.com> | Active |  | 6 | 3 |  | 2025-12-19 05:29 | 2025-12-19 05:27
5634 | Task | Internal call with Tejasvinee and Satin | Gawande, Ashwin <agawande@trustbridge.com> | Closed |  | 0.5 | 0.5 |  | 2025-12-19 05:33 | 2025-12-19 05:32
5635 | Task | RE: Testing Updates with Dr. Rutkowski - MAC AI | Patel, Hetal <hpatel@trustbridge.com> | Active |  | 10 | 8 | 0 | 2025-12-19 09:32 | 2025-12-19 05:38
5636 | Bug | Create new storm season form : date picker UI issue | Jain, Sakshi <sjain@trustbridge.com> | New | Frontend |  |  |  | 2025-12-19 06:24 | 2025-12-19 05:56
5637 | User Story | As a developer, need to create API to populate Workforce Master table from csv file | Sharma, Hemant <hsharma@trustbridge.com> | Active | Backend |  |  |  | 2025-12-19 07:11 | 2025-12-19 07:11
5638 | Task | Create an API to dump data from the csv to sql table | Sharma, Hemant <hsharma@trustbridge.com> | Active | Backend | 16 | 4 | 12 | 2025-12-19 09:45 | 2025-12-19 08:16
5639 | Task | Unit testing for US_5602 | Patil, Nishiket <npatil@trustbridge.com> | Closed |  | 2 | 2 |  | 2025-12-19 09:06 | 2025-12-19 09:06
5640 | User Story | As a user, I should be able to see information extracted from referral documents | Patil, Nishiket <npatil@trustbridge.com> | Active |  |  |  |  | 2025-12-19 09:10 | 2025-12-19 09:07
5641 | Task | [Dev] : Extract information from the referral documents for IntakeChannel - Fax | Patil, Nishiket <npatil@trustbridge.com> | Active |  | 20 | 0 | 0 | 2025-12-19 09:11 | 2025-12-19 09:11
5642 | Task | setup emergencyprep domain on test env | Sachin Mehta <smehta@trustbridge.com> | Closed |  | 4 | 5 |  | 2025-12-19 11:12 | 2025-12-19 11:11
5643 | Task | Code review for staging | Sachin Mehta <smehta@trustbridge.com> | Closed |  | 1 | 1 |  | 2025-12-19 11:15 | 2025-12-19 11:14
5644 | Task | Unable to add Patient to the waitlist in IPU bed board | Sachin Mehta <smehta@trustbridge.com> | Closed |  | 2 | 3 |  | 2025-12-19 11:16 | 2025-12-19 11:16
5645 | Task | Conducting Technical Sync-up call with Client 12/24 | Gawande, Ashwin <agawande@trustbridge.com> | New | Meeting | 1 |  | 1 | 2025-12-22 00:20 | 2025-12-22 00:20
5646 | Task | Collating all updates in PPT for technical sync-up meeting 12/24 | Gawande, Ashwin <agawande@trustbridge.com> | New | Planning | 2 |  | 2 | 2025-12-22 00:21 | 2025-12-22 00:21
5647 | Task | PPS Decision Tree Discussion - 12/22 | Gawande, Ashwin <agawande@trustbridge.com> | New | Meeting | 0.5 |  | 0.5 | 2025-12-22 00:29 | 2025-12-22 00:28
5648 | Task | Need to review wireframes for MAP view (Workforce) | Gawande, Ashwin <agawande@trustbridge.com> | New | Meeting | 2 |  | 2 | 2025-12-22 00:32 | 2025-12-22 00:30
5649 | Task | Need to conduct Phase 1 demo with Malathi and team for Emergency Portal | Gawande, Ashwin <agawande@trustbridge.com> | New | Meeting | 0.5 |  | 0.5 | 2025-12-22 00:36 | 2025-12-22 00:32
5650 | Task | Need to conduct Phase 1 demo with Emergency leadership for Emergency Portal | Gawande, Ashwin <agawande@trustbridge.com> | New | Meeting | 0.5 |  | 0.5 | 2025-12-22 00:39 | 2025-12-22 00:37
5651 | Task | Need to conduct Phase 1 demo with Internal team for Emergency Portal | Gawande, Ashwin <agawande@trustbridge.com> | New | Meeting | 0.5 |  | 0.5 | 2025-12-22 00:39 | 2025-12-22 00:39
5652 | Task | Need to have internal discussion for Training module | Gawande, Ashwin <agawande@trustbridge.com> | New | Meeting | 0.5 |  | 0.5 | 2025-12-22 00:56 | 2025-12-22 00:54
5653 | Bug | Same employee card is opening | Jain, Sakshi <sjain@trustbridge.com> | New |  |  |  |  | 2025-12-22 08:30 | 2025-12-22 08:27
5654 | Bug | The tooltip or need help (question mark) is not having the description | Jain, Sakshi <sjain@trustbridge.com> | New | Frontend |  |  |  | 2025-12-22 08:36 | 2025-12-22 08:34